## Basic Manual Gantt Chart (hidden)
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart
Autism App Planner
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete |  | Start Date in Number Form | 42705 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Conceptual Design | 2016-12-01 | 2017-01-28 | 58 | 52.2 | 5.8 | 90%
UI Design | 2017-01-15 | 2017-02-28 | 44 | 39.6 | 4.4 | 90%
iOS Implementation | 2017-02-15 | 2017-04-15 | 59 | 0 | 59 | 0%
Testing | 2017-04-01 | 2017-05-01 | 30 | 0 | 30 | 0%
[6 empty] | Key: | Calculated Cell |  |  |  | Manual Entry Cell
[7 empty] | These cells will be automatically calculated based on the inputs on other cells. |  |  |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration (hidden)
Autism App Planner
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42941 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Conceptual Design | 2017-07-25 | 2017-07-30 | 5 | 2.5 | 2.5 | 50%
UI Design | 2017-07-27 | 2017-08-01 | 5 | 3.75 | 1.25 | 75%
iOS Implementation | 2017-07-27 | 2017-08-04 | 8 | 2 | 6 | 25%
Testing | 2017-07-29 | 2017-08-06 | 8 | 8 | 0 | 100%
Delivarable | 2017-08-15 | 2017-08-23 | 8 | 6 | 2 | 75%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.